## Sheet1
|  | 14th | 15rh | 16th | 17th | 18th | 19th | 20th | 21st
Task | Lead | Tues | Wed | Thu | Fri | Sat | Sun | Mon | Tue
Create front & back end repos | bar: 14th
Team members test git branching | All | bar: 14th
Dev Wireframes | All | bar: 14th
Dev ERD | All | bar: 14th
Mongoose Model Set up | Isaac | bar: 14th
Deploy Heroku (https://ancient-garden-56671.herokuapp.com) | Jason | bar: 15rh
Finalized Mongoose Models | All | bar: 15rh
Finalized Auth Routes | Isaac | bar: 15rh
Created components for upload & create Art + Routes | Jason | bar: 15rh
Create Component for edit user (artist) | Steven | bar: 15rh
Connect Update artist front end with Back End (Route) | Steven | bar: 16th
Index Art Front End / Back End | Will | bar: 16th
Create (upload) Art Front End / Back End | Jason | bar: 16th
Update Art FE/BE | Will | bar: 18th to 20th
Destroy Art FE/BE | Will | bar: 18th to 20th
Edit Button => (Edit art or Delete Art) | Will | bar: 17th to 19th
Create Art Adds to Artist Array | Jason | bar: 17th to 19th
Index Artist FE/BE | Jason | bar: 16th to 19th
Show Artist FE/BE in my profile | Steven | bar: 17th to 19th
Show Art FE/BE (click art in all art go to art page) | Isaac | bar: 17th to 19th
add the link between view art and art view (bootstrap) | Jason | bar: 17th to 19th
Image Upload, Image Render | Jason, Steven | bar: 17th to 19th
upload art 422 error, do we need an error handler? | Jason
React form to send the file | bar: 20th
Fix Secrets with dotenv | Jason | bar: 20th
Home Page Carosel (not mvp) | bar: 20th
Home Page as random artwork from Art array | bar: 20th
Resubmittal
Handlebars | Isaac | bar: 20th
Readme
Profile links use name vs. id
Edit Artist Bug
Change Hash router to browser router
update show art file
Artist Tags (tag to a collection [comma seperated tags?] | bar: 20th
React Component Refactoring -> Refactor show art paragraphs
Website consolidation